## Slide 1
Key Factors of Success in the Management
of Large Research Infrastructure Projects
RAMIRI 2 Programme
Trieste, Italy, October 24th to 26th, 2011
Dr. Wolfgang Meissner
INTECH GmbH
Berlin/Germany
Notes: Dear Gentlemen,
Why do we have to talk about key success factors in the construction management of large Research Infrastructures or RIs?

## Slide 2
Excellent, motivated people are working in the construction of large Research Infrastructure (“RI”) projects.
Cost overruns ( up to > 100 %), time delays ( up to > 100 %) and changes of scope are reality
  in research (often)
  in industry (sometimes, too)
The overall situation:

## Slide 3: Actually built nuclear power plants are still facing high cost increases.
Chart: 
| USA Average (1966-1978) | Olkiluoto 3 (Finnland) | Flamanville 3 (France) | South Texas 3&4 planned (U.S.)
Datenreihe 1 | 759 | 2063 | 2063 | 3004
Datenreihe 2 | 1636 | 1250 | 1062 | 957
Costs in Euro/KW, status June 2010.
Example: Cost overruns per KW of selected nuclear build projects
+32%
+61%
+216%
Gain of experience:
Technical
…
Managerial
1), 2)
1)
1), 3)
2)
Estimates, projects in progress (South Texas construction not yet started)
Currency conversion date May 20th, 2010
Initial overnight estimate 2005, cost update in 6/2010
Sources: Arthur D. Little, “Nuclear New Build Unveiled”, * EDF, Press Release “H1 2010 Results”
Actual cost overrun (estimation)
Initial cost estimation
*

## Slide 4: Important aspects in the management of large RIs.
Governance
Management
Planning, Reporting & Controlling, Counter measures
Procurement
Aspects:
Governance
Management
Controlling
Procurement

## Slide 5
Engineers and scientists develop a basic concept of the RI with rough estimations
Political decisions demand fixed data
Ongoing project changes according to the project‘s conceptual development are not adequately considered (cost, time)
Consequence: the project starts and runs under optimistic assumptions/conditions
Situation (at the beginning):
Governance
Management
Controlling
Procurement

## Slide 6
Political agreement upon a „memorandum of common understanding“ with fixed shared understanding of the foreseen scope, schedule and cost together with a phase oriented approval process
Key Factor 1:
Governance
Management
Controlling
Procurement
Competent supervising boards must have clearly defined authority and responsibilities and powers of self-assertion
  to be able to control and to supervise the top management
  to immediately impact the project, whenever this is necessary
  to quickly resolve conflicts presented by the top management
Key Factor 2:

## Slide 7
Selection of the management team on the basis of project management and technical skills with large independence and authorization and with full responsibility.
The management must be challenged to achieve the project goals within the given cost and time frames
The supervising boards should implement independent scientific and technical audits and external, professional project control.
Key Factor 3:
Governance
Management
Controlling
Procurement

## Slide 8: The ITER project needs severe changes…
Costs in Billions of US $, 2010 adjusted
Example: ITER Cost increase
Source: Nature 465, page 532-533 (2010), online publication 28 May 2010
Governance
Management
Controlling
Procurement

## Slide 9
The project starts with limited resources (cash, personal).
Structures and processes still have to be defined and modified according to the project’s growing.
Situation (after the start):
Governance
Management
Controlling
Procurement

## Slide 10
A clear and structured organization with respect to its growth is necessary (structure and processes).
The management must ensure
  the implementation of full responsibility at every level
  direct, transparent reporting lines
  the full use of management and project tools
The project must install processes
  to decide quickly upon technical, cost and time aspects
  to react quickly on technical, cost and time deviations by elaborating and controlling necessary countermeasures
Key Factor 4:
Governance
Management
Controlling
Procurement

## Slide 11: In early phases component orientation and coordination dominate.
Organization dominated by component design and procurement
Example: Organizational chart (early phase)
Governance
Management
Controlling
Procurement
Procurement
Office
Project Coordination
In-Vessel Components
Magnet System
Cryostat
Machine control /operation preparation
Construction
Enterprise
…
Component type n
planar
Non planar
Coordination
Inner vessel
Outer vessel
Ports
Mechanical Structure
Central machine control
Component control
Machine Control
Cryogenics
Component type 1
Coils
Power Supplies
Electrical grounding
Gas inlet
Thermal insulation
Component colling
Control room & communi-cation
CAD support
LHe supply
Refrigerant storage
Current leads
Assembly
Integration planning
Periphery
Assembly
Tools
Metrology
Project
(Procurement phase)
Cross divisional function
Component orientated
Assembly orientated
Operating surveillance
Vacuum technics

## Slide 12: More cross divisional functions are necessary during completion.
Organization dominated by machine assembly
Example: Organizational chart (later phase)
Governance
Management
Controlling
Procurement
Project
(Assembly phase)
Quality Management
Assoc. Director Coordination
Project Coordination
Device components
Engineering
Assembly
Physics
Project Control
Documentation
Cryostat
Cryogenics
Design Office
Configuration Space Control
Design Engineering
Configuration Management
On-Site Co-ordination
Device Assembly
Periphery
Assembly Technology
Diagnostics
Heating I
Machine Control
In-Vessel Components
Power
Supplies
Design and Configuration
Development and Test
Instrumen-
tation
Heating 2
Unit 1
Unit 2
Device
Safety
Technical Services
Diagnostics-Engineering
Cross divisional function
Component orientated
Assembly orientated

## Slide 13
Costs and time aspects are roughly estimated at the project’s start.
Insufficient up dates are conducted in the following phases.
Sufficient contingencies in costs and time are often not foreseen or not accepted.
Situation (during construction):
Governance
Management
Controlling
Procurement

## Slide 14: Realistic Planning is necessary.
Costs and time schedules must clearly be defined and realistically planned for all project phases from the very beginning onwards.
The costs and time schedules must be estimated with appropriate precision according to the different approval phases.
Phase related contingencies must be provided.
Key Factor 5:
Governance
Management
Controlling
Procurement

## Slide 15: The more completion the more complexity, deeper knowledge and …contingency consumption!
Example: Development of machine design during project development
Approval phase: Concept
Procurement phase: Conceptual design
Assembly phase: Detailed design
Governance
Management
Controlling
Procurement

## Slide 16: Effective “online” systems for controlling and steering/counter steering must be consequently applied.
An always current, bottom-up planning, controlling and reporting system based on work breakdown structures and financial management tools is mandatory.
  This integrated system must show all the planned and actual, weekly updated data and the resulting deviations
Efficient project control and risk management systems have to be fully embedded in the project, covering technical, financial and schedule issues, together with the parallel development of mitigating measures in case of deviations. This is essential to allow the management
  to react immediately
  both internally and externally (for suppliers and in-kind contributors).
Key Factor 6:
Governance
Management
Controlling
Procurement

## Slide 17: Processes: Implementation of a comprehensive bottom up – Planning, Controlling and Reporting Process
Example: Wendelstein 7-X Fusion Reactor IPP/Greifswald:
Bottom up Planning Process
Planning of Work Packages
Resp. Officer
Resp. Officer
Resp. Officer
Div. Head
Project
Coord.
Boards
+
Resp. Officer
Resp. Officer
Resp. Officer
+
Approval or „Iteration“
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
+
Approval or „Iteration“
Approval or "Iteration“, (Automatically) Creation of Reporting
Top down: Budgeting
Bottom up planning during the period (in detail)
Div. Head
Group
Leader
Group
Leader
Group
Leader
Group
Leader
Governance
Management
Controlling
Procurement
+

## Slide 18: Planning- and controlling tools in combination with work breakdown structures (WBS) and different data flows.
Example: Functional Concept of Financial Planning- and Controlling Tools
Governance
Management
Controlling
Procurement
Output: planned data
Input:
approval information, SAP-data
Output: approval
Input:
actual plan, basic plan, actual, committments, deviations
Monthly Planing
Monthly approval of plans
Optional monthly planning and/or approval of deviations of basic plan
Monthly information according to structured input
Actions:
Dataflow:
Output: planning of revenues
18
Management Information System
(for General Director, supervising committees, etc.)
Div Head
Div Head
PC
Fin. Dpmt
Planningstool
Actual data of orders (monthly), purchase committments and budgets ERP (e.g. SAP)
Output: approval
Input:
actual plan, basic plan, actual, committments, deviations
Output: approval
Input:
actual plan, basic plan, actual, committments, deviations
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
Resp. Officer
GL
GL
GL
GL

## Slide 19: Action oriented work breakdown structures (WBS) are the basis … also for counter steering.
MS-Project file with detailed WBS with linked tasks and completion data.
Example: Comparison: Plan vs. Actual (weekly updated!)
Governance
Management
Controlling
Procurement

## Slide 20: Continuous calculation of plan deviations, automatically, weekly updated mitigate surprises and allow flexibility.
Output Monatsplanung
Experimente 5
Cash Outflow (Total Year)
in EURO
Budget
Delta Budget
Adjusted Budget
Delta Adjust. Budget/Forecast
Forecast = Actual (YTD) + Forecast (Rest o. year)
Thereof Purchasing Orders
Thereof Forecast
Thereof Actual
270.000
260.000
60.000
10.000
30.000
40.000
200.000
50.000
Stand Experimente 5:
Stand Verwaltung:
10.000
270.000
300.000
260.000
10.000
300.000
260.000
270.000
50.000
30.000
40.000
200.000
Budget
Delta Budget
Adjusted Budget
Delta adjusted Budge t / Forecast
Forecast = Actual (YTD) + Forecast
(Rest of the year)
Thereof Purchasing Orders
Thereof Forecast
Thereof Actual
Example xyz Company: Deviation variance baseline (budget/actual plan)
Anticipated under-usage of planned cash outflow. Observable at beginning of year for total year (analog for total project period)
=> Counter action !
Governance
Management
Controlling
Procurement

## Slide 21: Quick, easy and comprehensive reporting systems automatically generated: the basis for steering and counter steering.
Output-Examples for Management Information System
Plans (monthly, quarterly)
Wished detailed analyses: e.g. Earned Value
Customized project plans and overviews
Deviation analyses
Overall project view
Automatical generation on the basis of structured, fixed inputs
Governance
Management
Controlling
Procurement

## Slide 22
The project needs leading edge products, which can be delivered only by a very limited number of suppliers.
First of its kind components, technologies and production methods are specified not as detailed as necessary.
The project is expecting that the supplier is delivering the ordered component or service on the basis of the agreed specifications in time, in cost and in the expected quality. Surprises occur …
Situation (7):
Governance
Management
Controlling
Procurement

## Slide 23
The responsibilities of all suppliers for deliverables must be contractually fixed in a detailed way based on detailed specifications and drawings.
The project must have full access to all relevant information on a daily basis
  technical
  financial (probable exception: in-kind contributions)
  schedule related
The same planning and controlling tools should be applied as internally (technical, financial, schedule related, technical).
Key Factor 7:
Governance
Management
Controlling
Procurement

## Slide 24: The suppliers must be controlled and managed by the same tools as internally applied (e.g. weekly updated WBS)
MS-Project file with detailed work breakdown structure (WBS) with linked tasks and completion data.
Example: Comparison: Plan vs. Actual (weekly updated!)
Governance
Management
Controlling
Procurement

## Slide 25: Suppliers must be managed by in process control, operational milestones must be monitored weekly/monthly.
Example: Generic milestone trend analysis (MTA)
Governance
Management
Controlling
Procurement
Chart: 
| 39417 | 39448 | 39479 | 39508 | 39539 | 39569 | 39600 | 39630
#REF! | 1
#REF! | 1
#REF! | 1
#REF! | 1
Optimistic planning | 39539 | 39539 | 39548 | 39573 | 39588 | 39595 | 39610 | 39630
Good planning | 39630 | 39630 | 39627 | 39630 | 39643 | 39634 | 39631 | 39630
Report date
Milestone date

## Slide 26: Deviations (technical, schedule, cost) occur all the time: Counter steering behavior together with effective tools and processes is mandatory.
Example: Superconducting joints
e.g.: Design & Engineering:
Difference between “planned” (green) and “as-built” (red) data
Governance
Management
Controlling
Procurement

## Slide 27: Very important: Even running projects can be stabilized! Just do it !!
Chart: 
| 34305 | 35506 | 35914 | 36266 | 36447 | 37021 | 37323 | 37529 | 37699 | 37860 | 37864 | 38063 | 38287 | 38441 | 38651 | 38807 | 39025 | 39151 | 39361
Meilensteintrendanalyse | 37255 | 37255 | 37985 | 39081 | 39081 | 39081 | 40177 | 40908 | 40908 | 41090 | 40312 | 40312 | 40312 | 40365 | 40396 | 40405 | 40402 | 40402 | 40417
Milestone-Trend-Analysis
Example: Megaproject: Planned start of commissioning
INTECH Audit:
- Project deficits
- Revision of schedule
INTECH acting as an active project tutor
Planned start of commissioning
Year
Reduction of deficits
Schedule stabilization
New Scenario realistic,
not optimistic
Governance
Management
Controlling
Procurement

## Slide 28
All project members are confronted day by day with many different problems …
… nevertheless, these project members will create a leading edge Research Infrastructure of which the scientific world can really be proud !
Outlook:

## Slide 29
For further information: | 
Dr. Wolfgang Meissner Tel.: +49 172 3800261 meissner@intech-gmbh.de | 
INTECH GmbH www.intech-gmbh.de | 
29